Salt Lake Community College – Thayne Center (Thayne Center 2021)

Program Review Action Plan – March 2022

Revisions with VP & Interim AVP – April 2022

Definitions of Goals:

- Bruin Pantry

  - Funding & Staffing – Provide structure and support to Bruin Pantry.

  - Basic Needs Extraction – Provide structure and support to the Basic Need program, differentiated from Bruin Pantry services.

  - Collaboration & Visibility – Increasing awareness and usage of both Bruin Pantry and Basic Needs program.

- CES

  - CES participant experience – Provide structure and support to the CES program, particularly for independent participants (students who are not in an engaged department).  Differentiating support for independent participants, Engaged Faculty, and Engaged Programs.

  - Visibility & Pathways – Increasing awareness and completion of CES program.

- Community Partners

  - Match & prepare students – Increase participation in and readiness for students in the Community Work Study (CWS) program. Approach partnerships for their benefits to students as emerging leaders, with persistence/completion in mind.

  - Partner relationships – Strategizing communication to campus partners.

  - Thayne vs. SLCC partners – Differentiating Thayne Center’s role with community partners from the role played by other campus partners (namely, Engaged Learning Office (ELO) and Govt. & Community Relations (GCR).

  - Faculty & Academic Affairs – Transitioning faculty support to Community-Engaged Learning office.

| Goal | Action | Timeline | Progress |
| --- | --- | --- | --- |
| 1.1 Funding & Staffing | 1.1.a. Realign & create Coordinator for Bruin Pantry position | November 21, rehire April 22 | Completed |
|  | 1.1.b. Allocate consistent funding for person hygiene products | Pilot SP22, Launch FA 22 | In progress |
|  | 1.1.c. Explore PT student leader position for the Bruin Pantry | August 22 | In progress |
|  | 1.1.d. Update user data via domo on a monthly basis | March 22 | In progress |
|  | 1.1.e. Strategize new staffing options as AmericorpsVISTA ends | April 23 | Long-term |
| 1.2 Basic Needs Extraction | 1.2.a. Realign & create Coordinator for Basic Need position | November 21 | Completed |
|  | 1.2.b. Develop a short-term campus connection plan for new Basic needs program | February 22 | Completed |
|  | 1.2.c. Expand and continue to implement campus connection plan for Basic Need program | Ongoing | In progress |
|  | 1.2.d. Refine case management and referral strategies – Basic Need referral in MySuccess, BIT, other referral strategies | March 22 | In progress |
|  | 1.2.e. Track and report usage of Basic Needs. | Jan 23 & 24 | Long-term |
|  | 1.2.f. Identify gaps and future need | Jan 24 - 26 | Long-term |
| 1.3 Collaboration & Visibility | 1.3.a. Refine case management & referral strategies – Food insecurity referral in MySuccess | March 22 | In progress |
|  | 1.3.b. Establish semesterly meeting with Associate Deans Council to foster connection to faculty. | April 22 | Short-term |
|  | 1.3.c. Establish standard minimum Pantry network hours | Piloting SP/SU 22 | In progress |
|  | 1.3.d. Semesterly print and social media campaigns for Pantry, addressing stigma of use | Jan 23 | - Long-term |
| 2.1 CES participant Experience | 2.1.a. Assess & define certificate requirements, collaborating with Dean of Humanities | On going | In-progress |
|  | 2.1.b. Transition SLiCE program into CES peer mentor role. | On going | In-progress |
|  | 2.1.c. Update virtual resources for independent participants: program website, canvas page. | On going | In-progress |
|  | 2.1.d. Develop advising structure for independent participants. | On going | In-progress |
|  | 2.1.e. Create CES marketing strategies, including connections to campus partners. (overlap with 2.2.e) | Jan 23 | Long-term |
|  | 2.1.f. Develop transition points to CWS and AmeriCorps as funding opportunities for underrepresented students. | Jan 24 | Long-term |
| 2.2 Visibility & Access | 2.2.a. Define and maintain partnership with CEL office. (overlap with 3.3.a. and 3.4.a) | On going | In-progress |
|  | 2.2.b. In collaboration with campus partners, develop an onboarding plan for engaged faculty. | Jan 24 - 25 | Long-term |
|  | 2.2.c. Work with CEL to identify opportunities for new engaged departments. | Jan 24 - 26 | Long-term |
|  | 2.2.d. Identify community partners for CES program. (overlap with 3.2.d) | Jan 23 - 26 | Long-term |
|  | 2.2.f. Implement marketing plan (overlap with 2.1.e) | Jan 23 - 26 | Long-term |
| 3.1 Match & prepare students | 3.1.a. Develop and host training for students about work with partners via CampusGroups | Oct 22 | Short-term |
|  | 3.1.b. Develop a semesterly marketing campaign, push CWS roles via CampusGroups | Pilot Jan 22, Implement Sept 23 | In progress |
|  | 3.1.c. Develop “post COVID partner call” to share about student’s changing needs | Oct 22 | Short-term (SU 22) |
|  | 3.1.d. Identify other SLCC partners in DOSA and CDO that connect students to partners (overlap with 3.3.a.) | Nov 22 | Short-term |
|  | 3.1.e. Expand definition of service to “engagement” (overlap with 3.3.a.) |  | Long-term |
|  | 3.1.f. Build plan raising awareness for JEDI in student participants | Jan 23 | Long-term |
| 3.2 Partner relationships | 3.2.a. Realigned Coordinator Community Partners responsibilities under AD.CE. | Nov 21 | Completed |
|  | 3.2.b. Refine the “partner agreement” as an MOU. | July 22 | Short-term |
|  | 3.2.c. Streamline MOU process, utilize CampugGroups | Jan 23 | Long-term |
|  | 3.2.d. Connect with smaller community-based organizations, using HSI & JEDI lenses (overlap with 2.2.d.) | Jan 23 - 26 | Long-term |
|  | 3.2.e. Share with partners about differing work of each campus partner (e.g. CEL & GCR) (overlap with 3.3.a & 3.4.a) |  | Long-term |
| 3.3 Thayne vs. SLCC partners | 3.3.a. Discuss differentiation points with campus partners CEL, GCR, etc.- distinguishing TC as student focused (overlap with 2.2.a, 3.1.d, 3.2.e.. & 3.4.a.) | On going | In progress |
|  | 3.3.b. Research models for how partnerships are supported at comparable institutions. | July 22 | Short-term |
|  | 3.3.c. Explore staffing needs or cross-functional reporting needs with CEL and GCR | Jan 23 - 26 | Long-term |
| 3.4. Faculty & Academic Affairs | 3.4.a. Discuss differentiation point with campus partners CEL, GCR, etc. – distinguishing who is faculty focused (overlap with 2.2.a., 3.1.e., 3.2.e., & 3.3.a) | On going | In progress |
|  | 3.4.b. Communicate differentiation points with wider group of campus partners | July 22 | Short-term |
|  | 3.4.c. Coordinate with CEL on promotion to students of high-impact practice | Jan 23 | Long-term |